## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | David | Casey | Cuong | Kyle | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 12 |  | 2
|  | Design architecture | Project Manager |  | 12 |  | 2 |  | 2 | 0 |  |  | 2
| Requirements |  |  |  |  | 9 |  | 9 |  |  |  |  | 0
|  | Gather | Requirements Engineer |  | 2 |  | 3 |  | 2 | 1 |  |  | 3
|  | Analyze | Requirements Engineer | Joel, Jacob | 4 | 5 | 3 |  | 2 | 1 |  |  | 3
|  | Specify | Requirements Engineer |  | 3 |  | 3 |  | 1 | 2 |  |  | 3
| Documentation |  |  |  |  | 28 |  | 38.5 |  |  |  |  | 0
|  | Project Charter | Project Manager | Joel, Jacob | 2 | 6 | 3 |  | 0 | 3 |  |  | 3
|  | Release Plan | Project Manager |  | 2 |  | 3.5 |  | 0.5 | 3 |  |  | 3.5
|  | Requirements Document | Project Manager, Requirements Engineer | Joel, Jacob, Min, Kris, Adrian, Hamza | 5 | 8 | 6.5 |  | 0.5 | 6 |  |  | 6.5
|  | Project Plan | Project Manager, Developers |  | 5 |  | 8 |  | 0 | 6 |  | 2 | 8
|  | Architecture Document | Architect |  | 4 |  | 4 |  | 2 | 2 |  |  | 4
|  | Test Report | Tester |  | 8 |  | 7 |  | 1 | 6 |  |  | 7
|  | User Guide & System Admin Doc | Developers, Requirements Engineer |  | 2 |  | 6.5 |  | 0.5 | 5 |  | 1 | 6.5
Coding | [6 empty] | 0 | [5 empty] | 0
Iteration 1: | Development |  |  |  |  | 55 |  | 0 |  |  |  |  | 0
|  | Determine technology needs | Developer |  | 1 | [5 empty] | 1 | 1 | 2
|  | Research and learn new language and environment | Developer | Joel, Jacob, Hamza, Kris, Min, Adrian | 20 |  |  |  | 1 |  | 22 | 9 | 32
|  | Set up basic HTML/CSS for web pages | Developer | Joel, Jacob | 10 |  |  |  | 5 |  |  |  | 5
|  | Write basic SQL queries | Developer | Min | 10 |  |  |  | 10 |  |  |  | 10
|  | Implement classes | Developer | Min | 14 | [6 empty] | 12 | 12
|  |  | Developer | [8 empty] | 5 | 5
|  |  | Developer | [8 empty] | 8 | 8
|  |  | Developer | [8 empty] | 4 | 4
|  |  | Developer | [9 empty] | 0
| Analysis |  |  |  |  | 14 |  | 0 |  |  |  |  | 0
|  | System Testing | Tester |  | 4 |  |  |  | 1 | 1 |  |  | 2
|  | Bug fix as required | Tester, Developer | Min | 5 | [6 empty] | 1 | 1
|  | Evaluate needs for next iteration | Project Manager |  | 5 |  |  |  | 1 | 1 |  |  | 2
Total |  |  |  |  | 118 | 137 | 132.5 | 49.5 | 29.5 | 37 | 23 | 43 | 132.5