## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | David | Casey | Cuong | Kyle | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 12 |  | 2
|  | Design architecture | Project Manager | Hamza | 12 |  | 2 |  | 2 | 0 |  |  | 2
| Requirements |  |  |  |  | 10 |  | 6 |  |  |  |  | 0
|  | Analyze | Requirements Engineer | Joel, Jacob | 4 | 8 | 3 |  | 2 | 1 |  |  | 3
|  | Specify | Requirements Engineer | Joel, Jacob, Hamza, Kris, Min, Adrian | 6 | 12 | 3 |  | 1 | 2 |  |  | 3
| Documentation |  |  |  |  | 14 |  | 21 |  |  |  |  | 0
|  | Project Charter | Project Manager | Joel, Jacob | 2 | 6 | 3 |  | 0 | 3 |  |  | 3
|  | Release Plan | Project Manager | Joel, Jacob, Hamza, Kris, Min, Adrian | 2 | 3 | 3.5 |  | 0.5 | 3 |  |  | 3.5
|  | Requirements Document | Project Manager, Requirements Engineer | Joel, Jacob, Min, Kris, Adrian, Hamza | 5 | 18 | 6.5 |  | 0.5 | 6 |  |  | 6.5
|  | Project Plan | Project Manager, Developers | Joel, Jacob, Hamza, Kris, Min, Adrian | 5 | 6 | 8 |  | 0 | 6 |  | 2 | 8
Coding | [6 empty] | 0 | [5 empty] | 0
Iteration 1: | Development |  |  |  |  | 122 |  | 20 |  |  |  |  | 0
|  | Determine technology needs | Developer | Joel, Jacob, Hamza, Kris, Min, Adrian | 6 | 6 |  |  |  |  | 1 | 1 | 2
|  | Research and learn new language and environment | Developer | Joel, Jacob, Hamza, Kris, Min, Adrian | 24 | 18 |  |  | 1 |  | 22 | 9 | 32
|  | Set up log in page (front end) | Developer | Joel, Jacob | 14 | 6 |  |  | 5 |  |  |  | 5
|  | Set up home page for user (front end) | Developer | Joel, Jacob | 12 | 4 | 4 |  | 10 |  |  |  | 10
|  | Set up home page for admin (front end) | Developer | Joel, Jacob | 10 | 4 | 4 |  |  |  |  | 12 | 12
|  | Set up Edit Streaming Services page | Developer | Joel, Jacob | 4 | 2 | 2 | [5 empty] | 0
|  | Set up Edit TV shows page | Developer | Joel, Jacob | 4 | 2 | 2 | [5 empty] | 0
|  | Set up Report Problem Page | Developer | Joel, Jacob | 4 | 2 | 2 | [5 empty] | 0
|  | Set up view problem page | Developer | Joel, Jacob | 4 | 2 | 2 | [5 empty] | 0
|  | Set up Select TV Shows page | Developer | Joel, Jacob | 4 | 2 | 2 | [5 empty] | 0
|  | Set up view statistics page | Developer | Joel, Jacob | 4 | 2 | 2 | [5 empty] | 0
|  | Database ER diagram | Developer | Kris, Min | 10 | [6 empty] | 5 | 5
|  | Set up database/tables | Developer | Kris, Min | 12 | [6 empty] | 8 | 8
|  | Insert data for user and admin | Developer | Kris, Min | 2 | [6 empty] | 4 | 4
|  | Insert data for streaming services | Developer | Kris, Min | 8 | [7 empty] | 0
|  | Insert data for TV Shows | Developer | Kris, Min | 8 | [7 empty] | 0
|  | Implement classes | Developer | Hamza, Adrian | 12 | [7 empty] | 0
|  | Set up database connection | Developer | Hamza, Adrian | 8 | [7 empty] | 0
|  | Set up functionality for login page | Developer | Hamza, Adrian | 16 | [7 empty] | 0
| Analysis |  |  |  |  | 32 |  | 9 |  |  |  |  | 0
|  | System Testing | Tester | Joel, Jacob, Kris | 9 | 9 | 9 |  | 1 | 1 |  |  | 2
|  | Debug | Tester, Developer | Joel, Jacob, Hamza, Kris, Min, Adrian | 18 | 3 | [5 empty] | 1 | 1
|  | Evaluate needs for next iteration | Project Manager | Hamza | 5 | 4 |  |  | 1 | 1 |  |  | 2
Coding
Iteration 2: | Development
|  | Update HTML pages as required | Developer | Joel, Jacob | 10 |  | 2 |  | 2 | 0 |  |  | 2
|  | Set up functionality for login page | Developer | Joel, Jacob, Hamza, Adrian | 10 |  | 3 |  | 2 | 1 |  |  | 3
|  | Set up Edit Streaming Services functionality | Developer | Joel, Jacob | 8 |  | 3 |  | 1 | 2 |  |  | 3
|  | Set up edit tv shows functionality | Developer | Joel, Jacob | 8 |  | 0 | [5 empty] | 0
|  | Set up report problem functionality | Developer | Joel, Jacob | 6 |  | 0 | [5 empty] | 0
|  | Set up view reports functionality | Developer | Joel, Jacob | 4 |  | 0 | [5 empty] | 0
|  | Implement classes | Developer | Hamza, Adrian | 12 |  | 0 | [5 empty] | 0
|  | Database ER diagram | Developer | Kris, Min | 10 | [7 empty] | 0
|  | Set up database/tables | Developer | Kris, Min | 12
|  | Insert data for user and admin | Developer | Kris, Min | 2
|  | Insert data for streaming services | Developer | Kris, Min | 8
|  | Insert data for TV Shows | Developer | Kris, Min | 8
|  | Implement classes | Developer | Hamza, Adrian | 12
|  | Set up database connection | Developer | Hamza, Adrian | 8
|  | Set up functionality for login page | Developer | Hamza, Adrian | 16
| Analysis | [11 empty] | 0
|  | System Testing | Tester | Joel, Jacob | 10 |  | 3 |  | 0 | 3 |  |  | 3
|  | Debug | Tester, Developer | Joel, Jacob, Hamza, Kris, Min, Adrian | 10 |  | 3.5 |  | 0.5 | 3 |  |  | 3.5
|  | Evaluate needs for next iteration | Project Manager, Requirements Engineer | Joel, Jacob, Hamza, Kris, Min, Adrian | 5 |  | 6.5 |  | 0.5 | 6 |  |  | 6.5
[7 empty] | 0 | [5 empty] | 0
Total |  |  |  |  | 234 | 309 | 112 | 58 | 24 | 23 | 23 | 42 | 112