## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | David | Casey | Cuong | Kyle | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 12 |  | 2
|  | Design architecture | Project Manager | Hamza | 12 |  | 2 |  | 2 | 0 |  |  | 2
| Requirements |  |  |  |  | 10 |  | 6 |  |  |  |  | 0
|  | Analyze | Requirements Engineer | Joel, Jacob | 4 | 8 | 3 |  | 2 | 1 |  |  | 3
|  | Specify | Requirements Engineer | Joel, Jacob, Hamza, Kris, Min, Adrian | 6 | 12 | 3 |  | 1 | 2 |  |  | 3
| Documentation |  |  |  |  | 14 |  | 21 |  |  |  |  | 0
|  | Project Charter | Project Manager | Joel, Jacob | 2 | 6 | 3 |  | 0 | 3 |  |  | 3
|  | Release Plan | Project Manager | Joel, Jacob, Hamza, Kris, Min, Adrian | 2 |  | 3.5 |  | 0.5 | 3 |  |  | 3.5
|  | Requirements Document | Project Manager, Requirements Engineer | Joel, Jacob, Min, Kris, Adrian, Hamza | 5 | 18 | 6.5 |  | 0.5 | 6 |  |  | 6.5
|  | Project Plan | Project Manager, Developers | Joel, Jacob, Hamza, Kris, Min, Adrian | 5 |  | 8 |  | 0 | 6 |  | 2 | 8
Coding | [6 empty] | 0 | [5 empty] | 0
Iteration 1: | Development |  |  |  |  | 98 |  | 0 |  |  |  |  | 0
|  | Determine technology needs | Developer | Joel, Jacob, Hamza, Kris, Min, Adrian | 6 | [5 empty] | 1 | 1 | 2
|  | Research and learn new language and environment | Developer | Joel, Jacob, Hamza, Kris, Min, Adrian | 24 |  |  |  | 1 |  | 22 | 9 | 32
|  | Set up log in page (front end) | Developer | Joel, Jacob | 14 |  |  |  | 5 |  |  |  | 5
|  | Set up home page for user (front end) | Developer | Joel, Jacob | 12 |  |  |  | 10 |  |  |  | 10
|  | Set up home page for admin (front end) | Developer | Joel, Jacob | 10 | [6 empty] | 12 | 12
|  | Database ER diagram | Developer | Kris, Min | 10 | [6 empty] | 5 | 5
|  | Set up database/tables | Developer | Kris, Min | 12 | [6 empty] | 8 | 8
|  | Insert data for user and admin | Developer | Kris, Min | 2 | [6 empty] | 4 | 4
|  | Insert data for streaming services | Developer | Kris, Min | 8 | [7 empty] | 0
|  | Insert data for TV Shows | Developer | Kris, Min | 8 | [7 empty] | 0
|  | Implement classes | Developer | Hamza, Adrian | 12 | [7 empty] | 0
|  | Set up database connection | Developer | Hamza, Adrian | 8 | [7 empty] | 0
|  | Set up functionality for login page | Developer | Hamza, Adrian | 16 | [7 empty] | 0
| Analysis |  |  |  |  | 32 | [6 empty] | 0
|  | System Testing | Tester | Joel, Jacob, Kris | 9 |  |  |  | 1 | 1 |  |  | 2
|  | Debug | Tester, Developer | Joel, Jacob, Hamza, Kris, Min, Adrian | 18 | [6 empty] | 1 | 1
|  | Evaluate needs for next iteration | Project Manager | Hamza | 5 |  |  |  | 1 | 1 |  |  | 2
Total |  |  |  |  | 210 | 210 | 112 | 29 | 24 | 23 | 23 | 42 | 112
Iteration 2: | Development |  |  |  |  | 52 |  | 48 |  |  |  |  | 0
|  | Set up functionality for login page | Developer | Joel, Jacob | 10 |  | 8 |  | 5 |  |  |  | 5
|  | Set up functionality for add tv show and services | Developer | Joel, Jacob | 20 |  | 18 |  | 10 |  |  |  | 10
|  | Set up home page for admin (front end) | Developer | Joel, Jacob | 6 |  | 4 |  |  |  |  | 12 | 12
|  | Create primary keys and foreign keys in respective tables. | Developer | Kris, Min | 6 |  | 4 |  |  |  |  | 8 | 8
|  | Create slideshow for presentation | Developer | Kris, Min | 2 |  | 4 |  |  |  |  | 4 | 4
|  | Write queries for updating and deleting rows in tables. | Developer | Kris, Min | 8 |  | 10 | [5 empty] | 0
|  | Insert data for TV Shows | Developer | Kris, Min | 8 |  | 10 | [5 empty] | 0
|  | Implement classes | Developer | Hamza, Adrian | 12 |  | 8 | [5 empty] | 0
|  | Set up database connection | Developer | Hamza, Adrian | 8 |  | 4 | [5 empty] | 0
|  | Set up functionality for login page | Developer | Hamza, Adrian | 16 | 96 | 14 | 70 |  |  |  |  | 0
| Analysis | [6 empty] | 22 |  |  |  |  | 0
|  | System Testing | Tester | Joel, Jacob, Kris | 9 |  | 12 |  | 1 | 1 |  |  | 2
|  | Debug | Tester, Developer | Joel, Jacob, Hamza, Kris, Min, Adrian | 18 |  | 10 |  |  |  |  | 1 | 1
|  | Evaluate needs for next iteration | Project Manager | Hamza | 5 |  |  |  | 1 | 1 |  |  | 2
Total |  |  |  |  | 436 | 390 | 173 | 169 | 43 | 27 | 23 | 80 | 173
Iteration 3: | Development |  |  |  |  | 44 |  | 36 |  |  |  |  | 0
|  | Set up needed pages | Developer | Joel, Jacob | 20 |  | 16 |  | 5 |  |  |  | 5
|  | CSS style | Developer | Joel, Jacob | 6 |  | 8 |  |  |  |  | 12 | 12
|  | Set up network table and connect with shows | Developer | Kris, Min | 10 |  | 6 |  |  |  |  | 8 | 8
|  | Create network show linking table | Developer | Kris, Min | 8 |  | 6 |  |  |  |  | 4 | 4
|  | Add network functionality | Developer | Hamza, Adrian | 12 |  | 8 | [5 empty] | 0
|  | Set up functionality for update TV shows | Developer | Hamza, Adrian | 8 |  | 4 | [5 empty] | 0
|  | Set up functionality for delete TV shows and services | Developer | Hamza, Adrian | 16 | 96 | 8 | 56 |  |  |  |  | 0
| Analysis | [11 empty] | 0
|  | System Testing | Tester | Joel, Jacob, Kris | 9 |  | 9 |  | 1 | 1 |  |  | 2
|  | Debug | Tester, Developer | Joel, Jacob, Hamza, Kris, Min, Adrian | 18 |  | 16 |  |  |  |  | 1 | 1
|  | Evaluate needs for next iteration | Project Manager | Hamza | 5 |  | 3 |  | 1 | 1 |  |  | 2
Total |  |  |  |  | 640 | 626 | 224 | 353 | 52 | 31 | 23 | 118 | 224
Iteration 4: | Development |  |  |  |  | 40 |  | 38 |  |  |  |  | 0
|  | Set up menu to reflect user status (admin/user/anonymous) | Developer | Joel, Jacob | 8 |  | 10 |  | 5 |  |  |  | 5
|  | Set up page to show user's favorite tv shows | Developer | Joel, Jacob | 6 |  | 8 |  |  |  |  | 12 | 12
|  | Set up page to submit user's favorite shows | Developer | Joel, Jacob
|  | Update Tables | Developer | Min | 10 |  | 6 |  |  |  |  | 8 | 8
|  | Test Coding | Developer | Min | 8 |  | 8 |  |  |  |  | 4 | 4
|  | Debug | Developer | Min | 8 |  | 6
|  | Insert additional shows into database along with their Networks and Streaming Services | Developer | Kris | 10 |  | 8
|  | Insert additional streaming services into database | Developer | Kris | 10 |  | 10
|  | Set up functionality for update TV shows | Developer | Hamza, Adrian | 8 |  | 8 | [5 empty] | 0
|  | Set up functionality for delete TV shows and services | Developer | Hamza, Adrian | 16 | 96 | 14 | 88 |  |  |  |  | 0
| Analysis | [11 empty] | 0
|  | System Testing | Tester | Joel, Jacob, Kris | 9 |  | 12 |  | 1 | 1 |  |  | 2
|  | Debug | Tester, Developer | Joel, Jacob, Hamza, Kris, Min, Adrian | 18 |  | 16 |  |  |  |  | 1 | 1
|  | Evaluate needs for next iteration | Project Manager | Hamza | 5 |  | 4 |  | 1 | 1 |  |  | 2
Total |  |  |  |  | 842 | 858 | 275 | 535 | 61 | 35 | 23 | 156 | 275